Noor Path Event – Meeting Summary

Draft run of show

- 5:00–5:10 PM – Team and volunteers arrive at the hotel. Everyone in place by 5:10, no exceptions.

- Before 6:00 – Drivers pick up the blind participants and bring them to the venue. A welcoming team meets them at the entrance and guides them in.

- 6:00–6:30 – Arrival, check-in (QR code scan at registration), and opening remarks.

- 6:30–7:00 – Introductions and icebreaker.

- CEO presentation – The Noor Path story: why the name, what the app does, step by step.

- App download moment – QR codes on screen for Google Play and the App Store. Guests download, register, and open the menu inside the app.

- Product experience – Guests order from the in-app menu and volunteers bring the products to them. Two products were discussed (chocolate and biscuits came up). Runs alongside a coffee break with Arabic coffee and water.

- Table workshop – "Three things you should know about blind people."

- Survey – Short and easy, star ratings only, done right after the presentation.

- Networking – At the end of the event, plus a feedback wrap-up.

- Guided exit – Volunteers walk participants out the same way they came in.

- Media interviews with blind attendees and VIPs happen during the event.

What we discussed

- Volunteers: 17 so far, Split into three groups: backstage, crowd management, and hospitality. Content is a separate team.

- Training: Volunteers must be trained on how to guide and assist blind people before the event. Non-negotiable.

- Chain of command: Organizers take instructions from one person only. Nobody goes around that person straight to the organizers. After every meeting, a report goes to the group.

- Report format: Two pages, with the event timeline starting from 6:00 PM.

- Branding: The event runs under the company's name.

- Audience: We focus on blind participants, not kids. We can't serve both well, so we pick one. A rough 60/40 split of attendees was mentioned but needs to be locked in.

- Purpose check: A concern was raised that blind attendees shouldn't be used as a marketing prop. The app demo and the whole experience have to genuinely work for them, including voice accessibility.

- Gamification: Scan-to-complete steps in the app with a small gift as the reward. The gift idea was liked but the details are open.

- Content prep: Happens at the hotel, since our own team will be the ones speaking on stage.

- Budget: Costs are running high. Needs a closer look.